## Product Backlog
Work Items | Initital Estimate | Adjust Factor | Adjust Estimate | 1 | 2 | 3 | 4
Set up Git/Gradle | 2 |  |  | 2
Make a Login screen | 5 |  |  | 5
Add a logout feature | 6 |  |  | 6
Add a registration screen | 5 |  |  | 5
Set up Database | 5 |  |  | 5
Create User types | 20 |  |  | 20
Reporting Sale | 10 |  |  | 10
Registering Interest | 10 |  |  | 10
Friends | 15 |  |  | 15
Ratings | 10 |  |  | 10
Internal System Logic | 50 |  |  | 50
Map | 15 |  |  | 15

## Sprint Backlog
Tasks | Responsible | Status | 1 | 2 | 3 | 4
Team Contract | Team | Done | 2
Product Backlog | Suvrat | Done | 1
Sprint Backlog | Goutam | Done | 1
Initialize the Repo | Goutam | Done | 0.5
Create the Android Project | Suvrat | Not started | 2
Create Git Branches and finish M2 | Team and individual | Not started | 2
Import git into android project | Suvrat | Not started | 1
Create an opening or welcome screen which has options for Login and Registration | Suvrat | Not started | 2
Login Validation | Goutam | Not started | 2
Cancelling login | Karan | Not started | 2
Logout Feature | Abhishek | Not started | 1
Registration Feature | Bhavani | Not started | 1